### Minutes of Meeting (MoM)

Project: Digital Mobile App 
Date: July 28, 2026
Time: 4:50 PM - 7:29 PM (approx.)

### Attendees

| Name | Role / Organization |
| --- | --- |
| Y Y (Yusuf) | Project Sponsor / Management |
| Kumar | Technical Lead / Consultant |
| Prabhu RS | Project Manager (Client Side) |
| Prem | Technical Team (Developer) |
| SURENDER M | Attendee |
| Bharath | Attendee |

### 1. Business Context

The meeting was convened to address critical issues and scope gaps identified during the User Acceptance Testing (UAT) phase of the Digital Mobile App project. The core problem is that while the application was designed and developed as a mobile-only solution, the client now expects full, bi-directional synchronization and functionality parity with the existing Oracle EBS (ERP) system.

This includes rendering transactions in the EBS 'Self-Service HR' (SSHR) interface and allowing users to initiate or approve actions from either system. This requirement was not included in the original scope, leading to a significant dispute over additional effort and cost.

### 2. Key Discussion Points & Decisions

A. Digital App vs. EBS Synchronization (New Scope)

- Discussion: Kumar and Yusuf explained that the client's request to make the digital app and EBS system bi-directionally synchronized is a major new requirement.

- Key Argument: The original project scope was exclusively for a mobile application. The assumption was that users would transition to the mobile app, not maintain two parallel systems.

- Estimate: Kumar estimated that this new requirement would require approximately 250+ hours of development effort (approx. 10 hours per module for over 25 modules) plus additional time for comprehensive testing.

- Yusuf's Decision: Yusuf firmly stated that this is out of scope. He insisted on a separate Change Request (CR) to cover the additional development and costs. He mentioned he is already at a significant financial loss on the project and cannot absorb this work.

B. Technical Approach and Oracle Standards (The "Base Table" Debate)

- Discussion: A debate arose regarding how data is stored and updated. Prabhu argued that since the digital app updates the backend, the data should automatically appear in the EBS. Yusuf and Kumar countered that this is technically incorrect.

- Oracle Development Standards: Yusuf demonstrated and cited Oracle development standards that prohibit directly updating base (core) tables. Customizations must be done using custom tables and APIs.

- Explanation: Kumar explained that the digital app updates staging tables, which then trigger workflows. The EBS UI cannot natively display data from these custom tables without additional development (rendering).

- Conclusion: This is not a bug but a consequence of the initial design. Any attempt to fix this "render" issue would be a significant development task, not a simple fix.

C. Critical Issues Raised During UAT (Priorities)

The following issues were logged in Jira and require immediate attention and resolution from the technical team:

- Marital Status Display: The 'Marital Status' field is not displaying correctly in the app (e.g., value "Video" in backend but not showing).

- Civility/Identification Field: The 'Civility' field was updated incorrectly due to a developer (Prem) identifying the wrong database column (attribute), causing critical login/action failures for users.

- Leave Approval Workflow (Multi-Level): The digital app is routing all leaves through a single-level approval, while the client's EBS workflow for certain leave types (e.g., Annual Leave >20 days) requires multiple levels of approval (L1, L2, L3).

- Data Purging & Pending Notifications: The client reported that after deleting/canceling leave requests, pending approval notifications remain visible. Kumar clarified that simply deleting a notification does not resolve the underlying workflow issue.

D. Escalation and Project Risk

- The Ultimatum: Prabhu conveyed that the client's management is frustrated and may drop the entire project if these issues are not resolved.

- Yusuf's Counter: Yusuf highlighted his commitment (e.g., no invoices submitted for months) but remained firm that accepting the new scope is impossible without a formal CR. He offered to join a call with the client to explain the technical and contractual realities but reiterated his final decision.

- Outcome: A deadlock was reached on the major scope item. The project's continuation is at risk.

### 3. Action Items

| S.no | Action Item | Owner | Due Date |
| --- | --- | --- | --- |
| 1 | Resolve UAT Issues: Fix the following logged Jira issues as a priority: Marital Status, Civility Field (correct column), and Leave Approval Workflow (multi-level). | Prem (Developer), Kumar (Tech Lead) | ASAP (High Priority) |
| 2 | Provide Data Flow Documentation: Prepare a clear technical document showing exactly which tables (staging, base) are updated, which columns, and the internal data flow. This is to build trust with the client. | Kumar | To be specified |
| 3 | Investigate Notification Issue: Research and provide a detailed explanation of why pending notifications remain after data is "cleaned up" or rejected by the client. | Kumar | To be specified |
| 4 | Discuss VPN Access: Kumar requested a discussion with the client regarding direct VPN access to the system to aid in troubleshooting and development. | Prabhu | Within the next few days |
| 5 | Proceed with Formal CR: Initiate a formal Change Request (CR) process for the bi-directional synchronization requirement, including the full effort and cost estimates. | Prabhu, Yusuf | Pending discussion |

### 4. Next Steps

- Technical Team: The developers will prioritize and update the critical issues logged in Jira.

- Project Management: Prabhu will discuss the immediate UAT blocking issues with the client's technical and management teams. He will also attempt to present the technical arguments made by Yusuf and Kumar.

- Sponsor-Level Discussion: Both parties agreed that a high-level discussion with the client may be necessary to resolve the scope dispute. Yusuf agreed to participate if required.

- Future Meeting: A separate knowledge transfer session will be organized with Kumar to explain the complex Oracle EBS data structure to the project team and, if needed, to the client.