## Sheet3
Issue Key & Summary | Status | Assignee | Priority / Latest Activity
OH-88: Get Event Registrations API Not Returning Approved Records | Verifying | Surender Mulukala | Reassigned by Prem today. Note added regarding submitted requests needing to display from GetMyRequests and under "View Approval".
OH-116: Get document of records - Not returning all values | Verifying | Surender Mulukala | Prem updated status today; mentioned mime type, blob, and features are working and ready for closure review if clear.
OH-138: Employee pending actions: details are missing | In Progress | Kumar | Reassigned to Kumar by Gayathiri Senthilkumar today.
OH-139: GetEmployeePendingActions - remove self user | In Progress | Kumar | Created and updated by Kumar yesterday; sprint and rank assigned by Gayathiri today.
OH-89: Extend Leave API & Validation Issues | Open Discussions | Surender Mulukala / Kumar | Error Reported: Returns You can only take 2 Work From Home Days per month. and overlap errors during test validation. Pending use case clarification

## Sheet4
Issue Key & Title | Status | Primary Contributors | Summary of Recent Updates
OH-141: ApplyLeaveLocalEvent - ExtendLeave | VERIFYING | Kumar, Surender Mulukala | Status updated to VERIFYING and reassigned to Surender Mulukala. PL/SQL test scripts executed for ApplyLeaveLocalEvent and ExtendLeaveLocalEvent with successful workflow resets.
OH-140: ApplyLeavePermission - ExtendLeave | VERIFYING | Kumar, Surender Mulukala | Reassigned to Surender Mulukala and moved to VERIFYING. Verified ApplyLeavePermission and ExtendLeavePermission procedures with sample payload.
OH-142: Notify Team Mates | In Progress / Updated | Kumar, Surender Mulukala | Reassigned to Surender Mulukala. Added implementation details for XXOOREDO_PEOPLE_APPS.ActionNotifyTeamMate to notify teammates upon successful leave application.
OH-118: Workflow Forwarding Issues | In Progress / Under Review | Kumar, Surender Mulukala | Updated procedure ActionWorkflowForwardManager to prioritize employee number (emp_num) over username fallback when forwarding notifications.
OH-96: Emergency Contact – Delete API Required | DONE | Abhijeet Santosh Adhav, Prem | Verified details and closed ticket after validating transaction details for deletion.
OH-112: GetLeaveRequests Comments | Updated | Kumar | Added REQUESTOR_COMMENT and APPROVER_COMMENT output fields to GetLeaveRequests.
OH-138: Notification Details | Updated | Kumar | Clarified mapping for Requester Emp ID and Recipient Role fields in approval messages.
OH-144: Task Assignment | Updated | Gayathiri Senthilkumar, Bharath | Updated description, rank, sprint, and assigned to Kumar.

## Sheet2
Ticket | Summary / Issue | Key Update / Details | Assigned To / Action Requested
OH-140 | ApplyLeavePermission - ExtendLeave | Added request_id parameter in validateleavepermission. | Abhijeet Santosh Adhav (Requested to verify)
OH-141 | ApplyLeaveLocalEvent - ExtendLeave | Added request_id parameter in validateleavelocalevent. | Abhijeet Santosh Adhav (Requested to verify)
OH-136 | Dependent mismatch (ERP vs App) | ERP shows 2 dependents & 1 emergency contact, but app only displays 1 dependent & 1 contact. Status updated to TESTING. | Prem
OH-118 | Request Forward behavior | Confirmed request forward is working properly with employee number input. | Gayathiri Senthilkumar
OH-143 | GetDocumentType procedure update | Additional required input parameter added: p_country (e.g., 'Kuwait'). Documentation update needed. | Surender Mulukala (To validate and share feedback)
OH-96 | Ticket Closure / Deletion details | Abhijeet closed the ticket after verification; Prem supplied transaction deletion details earlier. | Closed

## Sheet1
Issue Key & Title | Status | Priority / Assignment Update | Summary of Critical Details & Findings
OH-172: Apply Leave – Implement Bi-Directional Integration | To Do | Active Development | Development completed for Basic OAF Page and Mobile Retrofit (XXOOREDO_PEOPLE_APPS.erpapplyleave); validation in progress.
OH-136: Dependent List Mismatch (6 in ERP vs 4 in response) | Verifying | Reassigned to Abhijeet Santosh Adhav | PL/SQL fix verified for getempdependants. Discrepancy confirmed to be a test environment data setup issue (Person ID 17805 vs test name).
OH-170: Getleaverequests - Absence Days & Hours Calculation | In Progress | Reassigned to Gayathiri Senthilkumar | Fixed logic to calculate ABSENCE_HOURS and set ABSENCE_DAYS = 0 for hourly leave types. Test payload verified for Local Org Event.
OH-165: Getleaverequests - Actual No. of Absence Days | Testing | Priority: Highest → High | Failed verification for NMTC local org leave request 3044. Awaiting developer confirmation on start/end time evaluation logic.
Reassigned to Kumar
OH-163: Duplicate Approval Workflow Entries Displayed | Testing | Status Updated | Technical clarification provided: Seba is a Post-Approver FYI recipient, not a Level-2 approver. Awaiting client decision on workflow rules.
OH-156: Phono/FT Group - Leave Accruals Balance | Testing | Priority: Highest → High | Status updated and priority adjusted for further validation in testing.
OH-142: Apply Leave – Teammate Notification | Testing | Priority: Highest → High | Priority downgraded from Highest to High.
OH-164: Duplicate Approval Workflow Entries in Leave Screen | Testing | Priority: Highest → High | Priority downgraded from Highest to High.
OH-140: Days Getting Wrong in Pending Actions | Updated | Active Review | Confirmed error message originates from ERP Fast Formula. Requires EBS validation.
OH-169: Approval Display Issues | Closed | Reassigned & Closed | Closed as duplicate/redundant. Ongoing tracking consolidated into OH-163.
OH-145: Getleaverequests Functionality Briefing | Closed | Reassigned & Closed | Closed after functional breakdown of XXOOREDO_PEOPLE_APPS_LEAVE.getleaverequests was provided.
🔴 High-Priority Tasks OH-163 (Testing): Confirmed Seba Al-Onaizi is a Post-Approver (FYI recipient) rendered in the standard EBS Approvers table. Action: Awaiting client decision on workflow rules. OH-140 (In Review): Root cause identified in the ERP Fast Formula. Action: Functional review and EBS validation ongoing. OH-141, OH-89, OH-146 (Active): High-priority tasks under active tracking.

## Sheet5
Issue ID | Topic / Description | Status & Priority | Key Action / Findings
OH-87 | GetMyRequests API – Not returning complete employee workflow requests | Testing | Priority escalated by Surender Mulukala; actively undergoing workflow response validation.
(Priority raised to Highest)
OH-170 | Extended Leave Details (ABSENCE_HOURS & ABSENCE_DAYS logic) | Validation In Progress | PL/SQL fix compiled by Kumar to dynamically calculate absence_hours and explicitly set ABSENCE_DAYS to 0 for hourly leaves.
OH-165 | NMTC Local Organization Leave calculation failure (Emp 3044) | Assigned to Kumar | Issue reported regarding start_time and end_time logic handling for NMTC local organization leave; currently being investigated.
OH-136 | Dependent API Discrepancy (6 in ERP vs 4 returned) | Verifying | Code fix verified in PL/SQL procedure (getempdependants). Concluded to be a test environment data configuration issue.
(Assigned to Sai Kiran Kommu)
OH-163 | Leave Approvers Workflow & FYI Recipient logic | In Progress | Clarified AME approval chain logic distinguishing primary approvers from Post-Chain FYI recipients. Consolidated from OH-169.
OH-172 | Leave Application Procedure (erpapplyleave) | Validation In Progress | Basic OAF Page and Mobile Retrofit updates completed; validation currently underway.
OH-140 | Wrong number of days calculation in Pending Actions | Pending Validation | Error message traced back to ERP Fast Formula; pending verification in EBS.
OH-145 | Core Leave History Engine (getleaverequests) breakdown | Closed / Resolved | Full engine breakdown documented for dual extraction (PER_ABSENCE_ATTENDANCES + HR_API_TRANSACTIONS); ticket closed.

## Sheet6
Issue Key | Summary / Topic | Priority & Status | Assignee | Recent Activity & Details
OH-173 | GetLeaveApproversAll - Wrong approvers list showing compared to EBS | Highest | Kumar | Escalated from High to Highest priority by Sai Kiran Kommu; file attached and description updated.
(To Do)
OH-174 | Leave Workflow / Approver Update | Highest | Kumar | Priority escalated from High to Highest by Surender Mulukala; status updated and supporting files attached.
OH-175 | GetLeaveApproversAll - Approver return rules based on leave type + duration | Standard | Sai Kiran Kommu | Newly created issue by Surender Mulukala to separate and handle approver workflow triggering.
(To Do)
OH-146 | Dependent Second-Level Approval Displays First-Level Approver Information | Verifying | Abhijeet Santosh Adhav | Reassigned to Abhijeet Santosh Adhav for pending action verification.
OH-140 | ApplyLeavePermission - ExtendLeave | Verifying | Abhijeet Santosh Adhav | Reassigned to Abhijeet Santosh Adhav for validation after pending action procedure updates.